## Part1.Task1
WS2 Project: Web Application for Open Source Media Searching
Increment | Activities
1 | Core System Setup and User Account Management - Objective: Set up the project’s basic architecture and foundational components. - Features: + Initialize the project structure (front-end, back-end, database). + Implement basic user authentication (login, sign-up, password reset). + Secure user data handling + Basic database setup for storing user account details and recent searches. + Develop REST API or GraphQL for user account operations (registration, login, etc.).
2 | Media Search Interface - Basic Search and Openverse API Integration - Objective: Set up the media search interface and integrate with Openverse API to allow users to search and retrieve media. - Features: + Integrate with Openverse API for searching and retrieving open licensed media + Basic search functionality (search bar, media thumbnails) + Display basic data for media results + Build front-end to display search results (grid/list view).
3 | User Interface Improvements - Objective:Implement functionality for users to manage their recent searches. - Features: + Store recent searches in the database for each user. + Implement functionality to retrieve and display recent searches. + Allow users to delete or save recent searches for future use. + Enable persistence of user search history (stored across sessions).
4 | Improvement in Search Features and Advanced Filtering - Objective: Add advanced search capabilities, allowing users to filter and sort results. - Features: + Implement advanced search options (e.g., filter by license, type, date). + Implement sorting options (e.g., by relevance, date, popularity). + Improve UI/UX with more advanced search controls (dropdowns, sliders). + Integrate additional APIs or services for extended media metadata (e.g., licensing details, media formats).
5 | Media Display and Playback - Objective: Enable the ability to play and display media directly from search results. - Features: + Implement media player (audio/video) for displaying and playing media results. Implement image preview and media display (e.g., images, video embeds). Enhance media metadata presentation (e.g., captions, playback time)..
6 | Software Engineering Best Practices – Architecture and Design Patterns - Objective: Implement software engineering best practices, focusing on modularity, scalability, and design patterns. - Features: + Refactor system architecture to use design patterns + Ensure modular code that is scalable and maintainable. + Implement clear separation of concerns (e.g., services, controllers, models).
7 | Containerization with Docker & Environment Setup - Objective: Implement containerization using Docker to ensure a consistent development and deployment environment. - Features: + Create Dockerfile(s) to containerize the application. + Configure Docker Compose to manage multi-container setups (e.g., front-end, back-end, database). + Ensure the application can be easily run in any environment using Docker containers.
8 | Automated Build and Deployment Strategy - Objective: Set up automated build and deployment strategies. - Features: + Integrate CI/CD pipelines (e.g., using Jenkins, GitHub Actions, or GitLab CI). + Implement automated build processes (compiling, testing, etc.). + Set up automated deployment to staging/production environments.
9 | Automated Testing Strategy - Objective: Implement automated testing to ensure the quality and stability of the application. - Features: + Write unit tests for key components (user account management, media search). + Implement integration tests for API interactions. + Set up test coverage tools and ensure tests run automatically on each build.
10 | Clean Code and Documentation - Objective: Ensure code is clean, maintainable, and well-documented for future developers. - Features: + Refactor code for clarity, consistency, and readability. + Write comprehensive comments and documentation (API docs, in-line comments). + Use proper naming conventions and file organization. + Provide instructions for future development and extensions (e.g, adding new media sources).
11 | Final Testing, Bug Fixing, and Deployment - Objective: Complete final testing and prepare the application for production deployment. - Features: + Perform user acceptance testing (UAT) to ensure all features meet requirements. + Conduct final bug fixes and optimize performance. + Deploy the application to production with monitoring tools.
12 | Documentation for Reuse and Extensions - Objective: Provide comprehensive documentation that enables future reuse and extension of the system. - Features: + Write documentation for reusing and extending the application (e.g., adding new features, APIs). + Provide API integration guides + Document architecture, design patterns, and key decisions made during development.

## Part2.Task2
WS2 Project: Web Application for Open Source Media Searching
Timeline
FEB |  |  |  | MAR |  |  |  | APR
1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Core System Setup and User Account Management | Media Search Interface - Basic Search and Openverse API Integration | User Interface Improvement | Improvement in Search Features and Advanced Filtering | Media Display and Playback | Software Engineering Best Practices – Architecture and Design Pattern | Containerization with Docker & Environment Setup | Automated Build and Deployment Strategy | Automated Testing Strategy | Clean Code and Documentation | Final Testing, Bug Fixing, and Deployment | Documentation for Reuse and Extensions